## User stories
| Main User Story | Sub-Task
1 | Theatre | Add Theatre
Delete Theatre
2 | screen | Add Screen
Delete Screen
Search Screen
3 | Show | Delete Show
Add Show
Search Show
Show all Shows
Show all shows in a theatre
4 | Movie | Add Movie
Delete Movie
Search Movie
5 | Booking | choose seats
calculate total costs
choose payment method
make payment
show ticket
cancel booking
6 | Seat | block seat
book seat
cancel seat
7 | Authentication | login
logout

## Naveen
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Theatre
1.1 | Add Theatre
1.1.1 | Html Page | 3
1.1.2 | Component | 1 | 1 | 2020-08-04
1.1.3 | Validations + Exception Handling | 1.5 | 2 | 2020-08-04
1.2 | Delete Theatre
1.2.1 | Html Page | 1
1.2.2 | Component | 1 | 1 | 2020-08-04
1.2.3 | Validations + Exception Handling | 1.5 | 1.5 | 2020-08-04
2 | Screen
2.1 | Add screen
2.1.1 | Html Page | 2
2.1.2 | Component | 1.5 | 1.5 | 2020-08-10
2.1.3 | Validations + Exception Handling | 1.5 | 1.5 | 2020-08-10
2.2 | Delete Screen
2.2.1 | Html Page | 1
2.2.2 | Component | 1 | 1 | 2020-08-10
2.2.3 | Validations + Exception Handling | 1.5 | 1.5 | 2020-08-10
2.3 | Search screen
2.3.1 | Html Page | 2
2.3.2 | Component | 2 | 2 | 2020-08-10
2.3.3 | Validation | 1 | 1 | 2020-08-10

## Bhavani
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Show
1.1 | Add show
1.1.1 | Html Page | 2
1.1.2 | Component | 1
1.1.3 | Validations + Exception Handling | 2
1.2 | Delete show
1.2.1 | Html Page | 1
1.2.2 | Component | 1
1.2.3 | Validations + Exception Handling | 0.5
1.3 | Search show
1.3.1 | Html Page | 1
1.3.2 | Component | 1
1.3.3 | Validations + Exception Handling | 3
1.4 | Show all shows
1.4.1 | Html Page | 1
1.4.2 | Component | 1
1.4.3 | Validations + Exception Handling | 1.5
1.5 | Show all shows in theatre
1.5.1 | Html Page | 1
1.5.2 | Component | 1
1.5.3 | Validations + Exception Handling | 1

## Shirisha
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Booking
1.1 | Choose seats
1.1.1 | HTML Page | 3
1.1.2 | Component | 1
1.1.3 | Validations + Exception Handling | 2
1.2 | calculate total costs
1.2.1 | HTML Page | 3
1.2.2 | Component | 1.5
1.2.3 | Validations + Exception Handling | 1.5
1.3 | payment method $ make payment
1.3.1 | HTML Page | 2
1.3.2 | Component | 1.5
1.3.3 | Validations + Exception Handling | 2
1.4 | show ticket
1.4.1 | HTML Page | 2
1.4.2 | Component | 1
1.4.3 | Validations + Exception Handling | 2
1.5 | cancel booking
1.5.1 | HTML page | 1
1.5.2 | Component | 1
1.5.3 | Validations + Exception Handling | 1

## Tejasri
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Alloted on day | Comments
1 | Movie
1.1 | Add Movie
1.1.1 | HTML page | 3
1.1.2 | Component | 1
1.1.3 | Validations + Exception Handling | 1.5
1.2 | Delete Movie
1.2.1 | HTML page | 2
1.2.2 | Component | 1.5
1.2.3 | Validations + Exception Handling | 1.5
1.3 | Search Movie
1.3.1 | HTML Page | 2
1.3.2 | Component | 1.5
1.3.3 | Validation + Exception Handling | 1.5
2 | Seat
2.1 | Block Seat
2.1.1 | HTML Page | 3
2.1.2 | Component | 2.5
2.1.3 | Validation + Exception Handling | 1
2.2 | Book Seat
2.2.1 | HTML Page | 2
2.2.2 | Component | 1
2.2.3 | Validation + Exception Handling | 2
2.3 | Cancel Seat
2.3.1 | HTML Page | 1
2.3.2 | Component | 2
2.3.3 | Validation + Exception Handling | 2